## Day Out of Days Template
DAY OUT OF DAYS
Header
Field | Value
Production | SALT FLATS
Based on schedule | Blue, 9/29/2026
Shoot days | 12, Mon 10/5 to Sat 10/17/2026 (Sun 10/11 off, not shown)
Prep days shown | Fri 10/2 (travel), Sat 10/3 (rehearsal)
Prepared by | Mina Park, 2nd AD
Code legend
Code | Meaning
SW | Start work. First work day.
W | Work
H | Hold. Paid, not working, between start and finish.
WF | Work finish. Last work day.
SWF | Start, work, and finish on the same day.
T | Travel day
R | Rehearsal day
D | Dropped. Off payroll between work periods, only where the contract allows.
PW | Pickup work. First work day after a drop.
(blank) | Not engaged
Cast
# | Character | Performer | Fri 10/2 | Sat 10/3 | D1 Mon 10/5 | D2 Tue 10/6 | D3 Wed 10/7 | D4 Thu 10/8 | D5 Fri 10/9 | D6 Sat 10/10 | D7 Mon 10/12 | D8 Tue 10/13 | D9 Wed 10/14 | D10 Thu 10/15 | D11 Fri 10/16 | D12 Sat 10/17 | Travel | Rehearsal | Work | Hold | Drop | Start | Finish | Paid days
1 | DELL | Marco Ybarra |  | R | SW | W | W | W | W | W | W | W | W | W | W | WF | 0 | 1 | 12 | 0 | 0 | 10/5 | 10/17 | 13
2 | JUNE | Tessa Quill | T | R | SW | W | H | W | W | W | W | W | W | W | W | WF | 1 | 1 | 11 | 1 | 0 | 10/5 | 10/17 | 14
3 | HOLLIS | Glenn Hardesty |  |  |  | SW | W | W | D | D | D | D | D | PW | WF |  | 0 | 0 | 5 | 0 | 5 | 10/6 | 10/16 | 5
4 | MARISOL | Ana Lucero | [14 empty] | 0 | 0 | 2 | 0 | 0 | 10/9 | 10/10 | 2 | bar: W W D to W W D
5 | DEPUTY PACE | Curtis Vail | [5 empty] | SW | H | W | H | H | W | H | H | WF | 0 | 0 | 4 | 5 | 0 | 10/8 | 10/17 | 9
6 | EARL | Ray Oberst | [14 empty] | 0 | 0 | 2 | 0 | 0 | 10/12 | 10/13 | 2 | bar: WF H to WF H
7 | NADIA | Priya Sandhu | [5 empty] | WF H: SWF | 0 | 0 | 1 | 0 | 0 | 10/12 | 10/12 | 1
8 | BEV | Donna Kell | [5 empty] | SW: SWF | 0 | 0 | 1 | 0 | 0 | 10/8 | 10/8 | 1
| Working that day |  | 0 | 0 | 2 | 3 | 2 | 5 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3
| Holding that day |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0
| TOTAL | [15 empty] | 1 | 2 | 38 | 6 | 5 |  |  | 47
Stunts, doubles, and background
# | Element | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | Days | Notes
S1 | Stunt double, Dell | D10: R; D11: SWF | 2 | Fight rehearsal at lunch D10
S2 | Stunt double, Hollis | D10: R; D11: SWF | 2 | Fight rehearsal at lunch D10
S3 | Stunt coordinator | D10: R; D11: SWF | 2 | Sc. 39
B1 | Background, diner patrons | D4: 6 | 1 | Sc. 16, 17
B2 | Background, Union Ave | D6: 4 | 1 | Sc. 28
Template by Storiara (storiara.com). Free to use and modify.